## Sheet1
Task | Start Date | End Date | Duration
Finalize group roles and designated tasks | 2021-03-30 | 2021-04-08 | 9
Start the timeline for project completion | 2021-03-30 | 2021-04-08 | 9
Finalize due dates for the week | 2021-04-08 | 2021-04-13 | 5
complete Final Report Sections 1-3 (Kylee and Austin) | 2021-04-13 | 2021-04-15 | 2
Design Sketches of Website Design Concept (Everyone) | 2021-04-13 | 2021-04-15 | 2
Source and Analysis of 1 Piece of Data (Everyone) | 2021-04-13 | 2021-04-15 | 2
Skeleton of Website (Jack) | 2021-04-13 | 2021-04-15 | 2
Work on Chart Creation/Coding (Kevin) | 2021-04-13 | 2021-04-15 | 2
User Stories Began (creating the WHO) (Everyone) | 2021-04-15 | 2021-04-18 | 3
Complete Final Report Sections 4-5 (Kylee and Austin) | 2021-04-18 | 2021-04-22 | 4
Website Pages Created and Design Layout Achieved (Jack) | 2021-04-18 | 2021-04-22 | 4
Data Completely Collects and Graph Started (Kevin) | 2021-04-18 | 2021-04-22 | 4
First Overview/Critique Session (Kylee) | 2021-04-18 | 2021-04-22 | 4
“About Us” Page Completed (Austin) | 2021-04-18 | 2021-04-22 | 4
Finish User Stories (Everyone) | 2021-04-22 | 2021-04-25 | 3
First Edits Complete from Critique Session (Everyone) | 2021-04-22 | 2021-04-25 | 3
Complete Final Report Sections 6-8 (Kylee and Austin) | 2021-04-25 | 2021-04-29 | 4
Website Completed (Jack) | 2021-04-25 | 2021-04-29 | 4
Graph Completed and Embedded into Website (Kevin and Jack) | 2021-04-25 | 2021-04-29 | 4
Pre-Final Critique Session (Kylee) | 2021-04-25 | 2021-04-29 | 4
Submit for Review | 2021-04-25 | 2021-04-29 | 4
Review Critique from Early Submission and Finalize Edits (Everyone) | 2021-04-29 | 2021-05-02 | 3
Submit Final Product (Report, Website Link, GitHub link, Trello Link) | 2021-04-29 | 2021-05-02 | 3
| 44285 | 44318